## Slide 1: Managing Time and Cost
This material is based on the Fifth Edition of the Guide to the Project Management Body of Knowledge (PMBOK® Guide) published by the Project Management Institute (PMI®) in 2013.
PMI and PMBOK are registered marks of Project Management Institute, Inc.

## Slide 2: Key Learning Outcomes
When you complete this course you will be able to:
Explain the uses and importance of a WBS
Show how a WBS can be used for bottom-up estimating
Describe three other methods for estimating
Describe how a WBS illustrates a progressive decomposition of work
Describe the steps required to move from a WBS to a project schedule
Explain what activity sequencing is and how it relates to schedule development
Explain the difference between effort and duration in schedule development
Describe a PDM diagram and its uses
Define what is meant by a critical path for a project
Define the CPI and SPI measures of project performance and progress and explain how they are used in analyzing the current state of a project
Describe the techniques called crashing and fast tracking
Define what is meant by earned value management
Identify the various processes, and how they relate, that lead to a project schedule, starting with the project requirements

## Slide 3: CONTENTS
Module 1: Process Groups and Knowledge Areas - Review
Module 2: The WBS – Basis for Time & Cost Planning
Module 3: Determining the Project Schedule
Module 4: Determining the Project Budget
Module 5: Controlling the Schedule and Budget
Appendix A: Possible Solution for Celebration Case
Appendix B: Another Case Study for WBS
Appendix C: More on the Critical Path Method (CPM)
Appendix D: More on Earned Value Management (EVM)
Appendix E: Some PMP-Style Practice Exercises

## Slide 4: Process Groups and Knowledge Areas -- A Quick Review --
MODULE 1

## Slide 5: Accomplishing Tasks through Processes
The PMBOK® Guide identifies a total of 47 fundamental project management processes
These processes are logically grouped in two complementary ways: by major process group and by project management knowledge area
There are five process groups
There are ten knowledge areas
The knowledge areas are integrated across various process groups

## Slide 6: The Five Process Groups Reviewed
The Initiating Process Group
  This group encompasses the set of processes that are performed at the beginning of a project to define the project at a high level and obtain the authorization necessary to commit resources to officially start the project
The Planning Process Group
  This group is engaged to establish the scope of the project -- what is inside and what is outside the project’s boundaries, and to refine the project objectives and plan a course of action that will achieve these objectives.
The Executing Process Group
  This group focuses on managing the performance of the planned work activities so that they will produce results that satisfy the project objectives.

## Slide 7: The Five Process Groups Reviewed (cont’d)
The Monitoring and Controlling Process Group
  This group is designed to monitor, track, review and adjust the project activities based on the performance being observed
  In addition, the monitoring and controlling process group will help identify and initiate needed changes to the project plan.
The Closing Process Group
  This group is used to finalize all the activities at the end of the project and formerly close the project

## Slide 8: The Ten Knowledge Areas
There are 9 major management activities plus the integration of all these throughout the project, and these comprise the ten fundamental knowledge areas of project management:
  Scope Management
  Time Management
  Cost Management
  Quality Management
  Human Resource Management
  Communications Management
  Stakeholder Management
  Risk Management
  Procurement Management
  Integration Management
S T C – triple constraints
Q H C S – team-oriented issues
R P I – overall project challenges
Memory Joggers

## Slide 9: The Five Project Management Process Groups
Monitoring &
Initiating
Closing
Planning
Processes
Executing
Processes
Processes
Processes
Controlling Processes
Project
Deliverables
Project Sponsor
Project
Inputs
Project
Records
Process Assets
End users
Project Boundaries
(Five Process Groups)
This diagram is adapted from the Guide to the
Project Management Body of Knowledge (PMBOK ® Guide), 5th Edition

## Slide 10: Process Groups are NOT Phases
Monitoring/Controlling Processes
Executing Processes
Closing Processes
Planning Processes
Initiating Processes
Time
Finish
Start
Level of Activity
Adapted from PMBOK® Guide
Process Groups Overlap

## Slide 11
Communications
Management
Plan Communications Management
Control Communications
Manage Communications
Knowledge
Areas
Initiating Planning Executing Monitoring/Controlling Closing
Integration
Management
Develop Project Management Plan
Monitor and Control Project Work
Perform Integrated Change Control
Direct and Manage Project Work
Close Project or Phase
Develop Project Charter
Scope
Management
Plan Scope Management
Collect Requirements
Define Scope
Create WBS
Validate Scope
Control Scope
Time
Management
Plan Schedule Management
Define Activities
Sequence Activities
Estimate Activity Resources
Estimate Activity Durations
Develop Schedule
Control Schedule
Cost
Management
Plan Cost Management
Estimate Costs
Determine Budget
Control Costs
Adapted from PMBOK® Guide
Human Resource
Management
Plan Human Resource Management
Acquire Project Team
Develop Project Team
Manage Project Team
Procurement
Management
Plan Procurement Management
Control Procurements
Conduct Procurements
Close Procurements
Risk
Management
Plan Risk Management
Identify Risks
Quantitative Risk Analysis
Qualitative Risk Analysis
Plan Risk Responses
Control Risks
Quality
Management
Plan Quality Management
Control Quality
Perform Quality Assurance
Project Management Process Groups
Stakeholder
Management
Identify Stakeholders
Plan Stakeholder Management
Manage Stakeholder Engagement
Control Stakeholder Engagement
Our Focus
In this Class

## Slide 12: The WBS – Basis for Time and Cost Planning
MODULE 2

## Slide 13: Why is Planning Hard?
Company culture (there’s no time)
We think it unnecessary (we know what we’re doing)
Human nature (we find it painful)

## Slide 14: Two Pain Curves
pain
time from start of
the project
with good planning
without good planning
From J. P. Lewis, Fundamentals of Project Planning
Which approach involves more total pain?

## Slide 15: What Does Project Planning Involve? - recalled
What must be done?
How will it be done?
Who will do the work?
How long will it take?
How much will it cost?
Work Plan
Resource Plan
Estimation
Managing
Time and Cost

## Slide 16: Recall Project Initiation is the Basis for the Plan
Business
Need
Project
Purpose
Project
Objectives
Agreed Upon By All
Stakeholders
our response to
reflecting
1
2
3
4
Basis for the Work Plan

## Slide 17: How Do We Go From Objectives to a Work Plan?
Analyze the objectives
Decide what work is required
Organize the work

## Slide 18: The Work Breakdown Structure (WBS) - recalled
Separates the project deliverable into constituent parts
Supports the decomposition of work into simpler components, allowing us to better manage complexity
Supports planning and assignment of responsibilities
Helps determine resource requirements
Assists in tracking status and progress

## Slide 19: The Work Breakdown Structure (WBS) - recalled
The WBS is arguably the single most important project management tool available
It evolves through an iterative analysis of the project’s objectives and scope
Involves a top-down approach: progressive decomposition of work
The team should participate in its development to secure buy-in

## Slide 20: The Work Breakdown Structure (WBS) - recalled
It becomes the foundation for:
  Schedule planning
  Estimating effort required
  Resource planning
  Assigning responsibility for accomplishing and coordinating work

## Slide 21: Putting It Together #1
Your team has been given the task of planning and executing a large event for your company. The day-long event (the first of its kind for your company) is intended to celebrate this year’s remarkable accomplishments in rolling out three new product lines and achieving the largest net revenues in the company’s 30-year history.
The event is to include a catered meal for all, several outside speakers, and presentations by representatives of the company’s three new product lines. All of the company’s 500 employees will be invited to attend. The company has no facilities capable of handling a crowd of this size, so an outside venue will have to be used. The company president has enthusiastically supported this concept. She has requested an estimate of the total expense of the event, to include not only the direct costs, but also the hours of labor expended by your team and other company employees you might engage to help you with the work. In addition, she also needs your best estimate for the earliest possible date for the event.

## Slide 22: Putting It Together #1
Create a Business Need and Project Purpose for this project
Based on the Project Purpose create a list of major Objectives for the project.
Once each team has presented, work as a group to arrive at a consensus Project Purpose and set of Objectives for the project.
Part 1:

## Slide 23: Putting It Together #1
Each team should now use the consensus Objectives to create a preliminary (high-level) task list for the project.
Once each team has presented, work as a group to arrive at a consensus high-level task list for the project.
As a group, validate this task list against the project objectives.
Part 2:

## Slide 24: Putting It Together #2
This activity continues with the project to deliver a company “celebration.” Each team should use the consensus Project Objectives and task list that the group has agreed to as the starting point for this activity.
Particularly, the job at hand in this activity is to:
Use the task list to create a WBS for the project. Use our Web self-service case study as a guide and example.
Display the WBS in a hierarchical graphical format
Once each team has presented, work as a group to arrive at a consensus WBS for the project.
Validate this WBS against the agreed-upon task list and the project objectives.

## Slide 25: Recall the WBS as an Effort Estimation Tool
The WBS enables a bottom-up estimating approach
Bottom-up estimating is appropriate when we have a good handle on work decomposition
It works on the premise that the effort required for smaller tasks can be more accurately estimated than the effort required for larger ones

## Slide 26: WBS and Effort Estimation -- recalled
We define work packages as those at the bottom of the WBS – with no subtasks of their own
Estimate all the work packages first
Rollup these estimates (add them) to get estimates for higher-level subtasks
In this way you can derive an overall estimate, as well as estimates for subsystems at various levels

## Slide 27: The WBS as a Work Organizer
The basic rationale for creating a WBS is to organize the work already identified in the task list
However, the task list, by its nature, focuses on project objectives and deliverables – not on what may be required to organize the necessary effort
In deriving the WBS, the necessary organizing effort must also be included:
  Group the tasks
  Add new tasks to provide organizing structure
Account for the project management tasks as well

## Slide 28: Putting It Together #3
Use the WBS to create a bottom-up estimate for total cost (including hours of employee labor) for the project.
Use the WBS to create and agree to a work assignment matrix for your team. Note: you are only concerned with who will be responsible for what – you are not scheduling the actual work yet; that will come later.
This activity continues with the project to deliver a company “celebration.” Each team should use the consensus WBS that the group has agreed to as the starting point for this activity.
Particularly, the job at hand in this activity is to:

## Slide 29: Determining the Project Schedule
MODULE 3

## Slide 30: Work Planning Asks …
What must be done?
How will it be done?
Who will do it?
How long will it take?
How much will it cost?

## Slide 31: Strategies for Effective Work Planning
Plan for planning
  Good plans aren’t developed on an ad hoc basis
  Planning sessions should be carefully planned
The persons who will work the plan should participate in its development
Expect to change the plan
  Conditions change
  New information is discovered
Ensure a good foundation
  Accurate and clear Business Need and Project Purpose statements
  SMART objectives

## Slide 32: Time Management
According to the PMBOK® Guide, the Project Time Management knowledge area includes the processes required to manage the timely completion of the project
There are six constituent Time Management processes within the Planning process group, and as we will see, these all contribute to and culminate in the process Develop Schedule
  Plan Schedule Management
  Define Activities
  Sequence Activities
  Estimate Activity Resources
  Estimate Activity Durations
  Develop Schedule
The 7th Time Management process named Control Schedule is within the Monitoring/Controlling process group
See the diagram on Slide 12 for an overview of the Time Management Processes and how they relate to the Process Groups

## Slide 33: Time and Cost Planning Processes
Create WBS
Define
Activities
Acquire Project Team
Sequence
Activities
Estimate
Activity Duration
Develop
Schedule
Estimate
Costs
Estimate
Activity Resources
Determine
Budget
Scope Mgmt
Time Mgmt
Cost Mgmt
Human Resource Mgmt
Knowledge Areas
Define
Scope
Collect
Requirements
Adapted from PMBOK® Guide

## Slide 34: Creating a Complete Schedule
The WBS is the starting point in the construction of a schedule
With the WBS in hand, we have:
  the activities (tasks) to be done
  the hierarchical organization of these activities
  a bottom-up estimate of the effort required
What’s missing?

## Slide 35: The WBS Doesn’t Provide:
Precedence or sequencing information for activities
The ability to prioritize activities for the timely completion of the project
The ability to organize and track the schedule of project activities

## Slide 36: Additional Schedule Planning Tools
Precedence Diagramming Method (PDM) network diagrams
  Precedence or sequencing information for activities
Critical Path Method (CPM) Diagrams
  Ability to predict which activities are of higher priority for the timely completion of the project
Gantt Charts
  Ability to schedule and track project activities
  Information needed to make optimal resource allocations

## Slide 37: Precedence Diagramming Method Diagrams
The PDM diagram captures predecessor or sequencing information for all activities (tasks) in the WBS
Used as an intermediate step toward a CPM diagram
Work Breakdown Structure
PDM Diagram

## Slide 38: PDM Network Diagram
Activity M
Activity P
Activity N
Activity O
Activity Q
Activity R
Activity S
Activity N must complete before Activity R can begin, and so on.
Captures logical relationships among the project activities (tasks)

## Slide 39: Putting It Together #4
This activity continues with the project to plan and execute a company “celebration.” Each team should begin the exercise with the consensus WBS that the group has agreed to earlier.
Create a PDM network diagram for the project. Note that the PDM network diagram is intended to capture only the logical relationships among the various activities – not the project schedule.
Once each team has presented, agree on a consensus PDM network diagram.

## Slide 40: CPM Diagrams
CPM Diagrams are derived from PDM Diagrams
To accomplish this, we must translate effort estimates into duration estimates
Critical Path Method (CPM) Diagram
PDM Diagram

## Slide 41: Effort and Duration
Effort defines the amount of work required to complete a activity (often measured in hours)
Duration refers to the calendar time required to complete activity (often in days or weeks)

## Slide 42: Effort and Duration (cont’d)
Effort is distributed over a duration
This is done by assigning some particular number of persons to the activity at various times
Or, we can assign percentages of one or more persons’ time to the activity at various times
Requires knowledge of the activity plus human resource planning

## Slide 43: Effort, Duration, and Resource Allocation
For example, a 750 hour effort would have a 10-week duration if 2 persons were allocated to it fulltime (assuming a fulltime week = 37.5 hours) for that period
However, this same effort could result in drastically different durations, with different resource allocations:
  40 weeks – if 50% of a person’s time is allocated to it
  20 weeks -- if 1 person is allocated to it fulltime
  15 weeks -- with1 person fulltime for 10 weeks, then 2 persons fulltime for the next 5 weeks
  5 weeks – with 4 persons allocated to it fulltime

## Slide 44: Effort, Duration, and Resource Allocation (cont’d)
It is important to remember that the required effort is just one factor that goes into making a duration estimate. Some activities have limited possibility for compression.
We’ve all heard it:
If one woman can produce a baby in 9 months, how soon can 9 women produce a baby?

## Slide 45: Float or Slack Time
If an activity can be completed before it is absolutely necessary for other activities waiting for it, we say that we have built float or slack time into our schedule
Float adds flexibility to a project’s schedule
The Critical Path Method (CPM) Diagram captures this feature of a project

## Slide 46: CPM Diagrams Add Information to the PDM Diagram Nodes
Activity
Earliest
Start
Earliest
Finish
Duration
Float
Latest
Start
Latest
Finish
Add this information for each node
in the Precedence Graph
Critical Path Method (CPM) Diagram
PDM Diagram

## Slide 47: Creating CPM Diagrams
Optional: Appendix C Explains and
Demonstrates CPM Calculations

## Slide 48: Critical Paths
If an activity with 0 float slips, the entire project will slip by that amount
This is why activities that have 0 float are said to be on a critical path
There may be multiple critical paths for a project
Many practitioners establish some threshold amount of float (suitably small) and compute near-critical paths as well
Photo by Alistair Williamson

## Slide 49: Gantt Charts
Created from CPM diagrams
Captures scheduling information in a bar chart format
Dynamic Gantt charts (that is, those that are updated frequently) are an excellent tool to ascertain the status of a project at a given time
Good tool for estimating resource needs in a given time frame
Critical Path Method (CPM) Diagram
Gantt Chart

## Slide 50: Gantt Chart – An Example
activities
T1
T2
T3
T4
T5
date (week #)
1 2 3 4 5 6 7 8
critical
path
float

## Slide 51: Why is the Critical Path Important?
Can be used to focus resources and attention more efficiently and effectively
Best resources can be assigned to critical path activities
Allows project manager to monitor crucial activities more closely
Helps prioritize risks, so risk mitigation activities can be focused on the most important potential risk events
As noted, “near-critical” activities can also be identified and tracked

## Slide 52: Adjusting for Schedule “Emergencies”
Schedule emergencies can be addressed by crashing or fast-tracking critical path activities
Crashing means compressing activity durations
Fast-tracking means doing things in parallel
The danger in both crashing or fast-tracking is increased risk

## Slide 53: Determining a Project Budget
MODULE 4

## Slide 54: Cost Management
According to the PMBOK® Guide, Project Cost Management knowledge area includes the processes involved in planning, estimating, budgeting, financing, funding, managing, and controlling costs to complete the project within the approved budget
There are three constituent Cost Management processes in the Planning process group
  Plan Cost Management
  Estimate Costs
  Determine Budget
The 4th Cost Management process is called Control Costs and by its name it is clear that it is included within the Monitoring/Controlling process group
Review the diagram on Slide 12 for an Overview of the Cost Management Processes and how they relate to the Process Groups

## Slide 55: Note on Cost Management
We should note that such things as the level of accuracy to be used for cost estimates, the units of measure (for example, hours, days, weeks, etc. for effort), the control accounts to be used in conjunction with the WBS (if applicable) are all environment specific and hence will not be a part of our discussion

## Slide 56: Estimating
The PMBOK® Guide identifies four important estimating techniques
  Analogous estimating
  Parametric estimating
  Bottom-up estimating
  Three-point estimating
All can be useful depending on the circumstances

## Slide 57: Analogous (Top-Down) Estimating
Analogous estimating uses information from previous similar projects as a basis for estimating the current project
When estimating costs, the technique relies on the actual costs of previous similar projects (not the estimated costs) as a basis for estimating the cost for the current project
Of course some adjustments may need to be made when applying historical information to the current project which will be in many ways different from any project done before
Analogous cost estimating while generally less costly and less time-consuming to apply than other techniques, is also generally less accurate
It may be more useful in the earlier phases of the project then later phases, when we have more project information available

## Slide 58: Parametric Estimating
Parametric estimating uses a statistical relationship between historical data and other variables called parameters to calculate estimates for activities.
These parameters might include such things as square footage in building construction, or lines of code in software development
This technique can produce more accurate estimates than analogous estimating provided that the underlying data built into the statistical model being used is accurate and applies to the current project

## Slide 59: Bottom-Up Estimating
Bottom-up estimating is one of the most common and most reliable methods of estimating
Its use depends on having a good understanding of the components of the work to be done
As we have seen, the WBS is a primary artifact used in bottom-up estimating
Recall that the advantage this approach accrues from the progressive decomposition we do in a WBS because it is usually much easier to estimate the cost of work packages accurately, than to estimate larger work components accurately
The accuracy of the method is further improved when we get the people who will actually be responsible for the work being estimated involved in providing the estimates

## Slide 60: Three-Point Estimating
The three-point estimating technique relies on taking a weighted average of three separate estimates
Usually you would employ
  A most likely estimate
  An optimistic estimate
  A pessimistic estimate
A popular technique that employs three-point estimating is PERT (Program Evaluation and Review Technique), pioneered by the US Navy in the Polaris Submarine Missile Program. PERT calculates an expected project activity cost using such a weighted average.

## Slide 61: Contingency Reserves
An additional tool that can be used in estimating costs is called reserve analysis
This usually includes including contingency reserves to account for the uncertainty in cost estimation.
Such reserves can be calculated as a percentage of the total estimated cost (often called management reserves)
As better information about the project becomes available, the contingency reserve may be used or reduced or even eliminated
When this tool is used, contingencies should be clearly identified as such in the cost documentation.

## Slide 62: Cost of Quality
A possible input for cost estimating are assumptions about the cost of quality (COQ)
There are two major categories of quality, called the cost of conformance and the cost of nonconformance
The cost of conformance is estimated based on the activities in the project designed to create a quality product
The cost of nonconformance, which includes such things as rework or scrap work, is very difficult to estimate and is often overlooked when project costs are estimated
However, it is wise to include some assumptions about the cost of nonconformance in the original project cost estimates, especially in software projects
More on this topic later in this series, when we consider the
Quality Management Knowledge Area

## Slide 63: Outputs of the Estimate Costs Process
There are two major outputs for the Estimate Costs process
  Activity cost estimates
  The basis for these estimates.
The basis for the estimates should include enough supporting documentation to indicate clearly how cost estimates were derived
This allows those using the estimates to better understand their possible accuracy

## Slide 64: Updating Estimates
Cost estimates should be refined throughout the project as more information about the project work becomes available
As a rough rule of thumb, cost estimates given early in the project life cycle -- rough order of magnitude (ROM) estimates -- could have an accuracy range of as much as plus or minus 50%
  This means an estimate of 10,000 hours could be reflected by an actual cost anywhere in the range 5,000 to 15,000 hours
Later as project information improves, cost estimates should converge toward a plus or minus 10% accuracy range
  This means a 10,000 hour estimate could be reflected by a true cost of between 9,000 and 11,000 hours
Organizational environments will differ as to what accuracies are acceptable at various points in a project
The project sponsor’s sensitivity to estimate accuracy will always be a factor too, of course

## Slide 65: Determining a Budget
The Determine Budget process basically combines, or aggregates, the estimated costs of individual activities or work packages
The primary inputs for the Determine Budget process are:
  Activity cost estimates
  Associated basis of those estimates
  Scope baseline containing
    Scope statement
    Work breakdown structure (WBS)
The main output of the Determine Budget process is the establishment of an authorized cost baseline for the entire project
This baseline includes all authorized budgets, but excludes any management reserve
Cost performance in the project will always be measured against the authorized cost baseline

## Slide 66: Monitoring the Schedule and Budget
MODULE 5

## Slide 67: Project Planning and Monitoring/Controlling
With no plan, it is all but impossible to control the parameters of a project
James Lewis calls planning and monitoring/controlling the Siamese twins of project management – codependent upon one another and inseparable
Monitoring/controlling involves tracking progress against a plan and modifying the plan when variances are observed

## Slide 68: Controlling the Project
Control is exercised by comparing where you are to where you are supposed to be so that corrective action can be taken when there is a deviation.
From J. P. Lewis, Fundamentals of Project Planning

## Slide 69: The Control Schedule Process
Controlling the schedule is the process of monitoring the status of the project to update project progress and manage changes to the schedule baseline.
Important inputs for the Control Schedule process
  Project plan, especially the schedule baseline and the schedule management plan
  Project schedule
  Work performance data
  Organizational process assets such as
    Formal or informal schedule control procedures and guidelines
    Schedule control tools (like MS Project)
    Monitoring and reporting methods.

## Slide 70: The Control Schedule Tools and Techniques
There are a number of tools or techniques for the Control Schedule process, including
  Performance reviews
    Trend analysis
    Critical Path Method (CPM)
    Variances which are differences in actual and expected results
      Often calculated using Earned Value Management (EVM)
  Project management software
  Resource leveling
  Schedule compression
  Use of a scheduling tool (like MS Project)

## Slide 71: Controlling and Planning
No plan, no control
Predicting the future is easy, it’s knowing what’s going on now that’s hard
J. P. Lewis
Fritz R. S. Dressler
Control is exercised by comparing where you are to where you are supposed to be so that corrective action can be taken when there is a deviation.

## Slide 72: Earned Value Management (EVM) (Knowing Where We Are Now)
According to the PMBOK® Guide:
“Earned value management is a management methodology that combines scope, schedule, and resource measurements to assess project performance and progress.
Refer to Section 7.4.2.1 for more details.

## Slide 73: Earned Value Management Definitions of Terms
Planned Value (PV): the authorized budget assigned to the scheduled work. The total planned value for the project is kn own s the Budget at Completion (BAC).
Earned Value (EV): the value of completed work expressed in terms of the approved budget assigned to the work that has been performed.
Actual Costs (AC): actual costs incurred to accomplish the work that gives earned value.

## Slide 74: Earned Value Management Derived Values
Schedule Variance: SV = EV - PV
Schedule Performance Index: SPI = EV/PV
Cost Variance: CV = EV - AC
Cost Performance Index: CPI = EV/AC
Hint for remembering formulas – all the right hand side expressions begin with the term EV.

## Slide 75: Using CPI and SPI for Project Status
A CPI of less than 1 indicates that the project cost are over budget; a CPI greater than 1 indicates that the project is running under budget. Do you see why? Remember CPI = EV/AC.
For example, a CPI of .75 would indicate that you are getting 75 cents of value for every dollar you are spending.
An SPI of less than 1 indicates that the project schedule is behind; an SPI greater than 1 indicates that the project is running ahead of schedule. Do you see why? Remember SPI = EV/PV.
For example, a CPI of .75 would indicate that you are progressing at a rate of 75% of the rate you planned.
Hint for remembering: larger is better in both CPI and SPI. Over 1 is good, below 1 is bad.

## Slide 76: Putting It Together #5
What is your cost variance and your CPI?
What do these calculations tell you about your project?
What is your schedule variance and your SPI?
What do these calculations tell you about your project?
What actions might you consider at this point?
You have just received updated progress reports on the project you are managing. The project’s budget is 2000 hours. Your project plan calls for you to have completed work at this point in time which was budgeted to require a total of 800 hours. The work that you have so far completed was budgeted for a total of 600 hours. The number of hours you have charged against the project budget to date is 900.

## Slide 77: Monitoring Involves Measurement and Modification
Major outputs of the Control Schedule and Control Cost Processes are
  Delivery time forecasts
  Budget forecasts
  Plan updates
    Schedule baseline
    Budget baseline
  The use of a change control process to make corrective changes in reaction to performance measures
  Other project changes requests

## Slide 78: A Possible WBS for the Celebration Case
Appendix A

## Slide 80: Another Case Study Developing a WBS
Appendix B

## Slide 81: Developing a WBS – A Case Study
Business Need: The costs of services provided by the Help Desk Group within a hypothetical company’s Technical Services Unit (TSU) has become too high in the opinions of the Director of the TSU and the VP who has oversight of the TSU. They believe the TSU must find a way to provide and promote an effective self-service adjunct to the Help Desk Group’s personal service component in order to reduce these costs.
Project Purpose: To create a self-service Web site to reduce demand for the personally-delivered services of the Help Desk Group within the TSU. The delivered Web site will have a look-and-feel consistent with the TSU’s main Web site. It will organize self-help information in an attractive, appealing, and easily navigable way. The presentation of the site will be separated from its content insofar as possible in order to enhance future maintenance and enhancements to the site.

## Slide 82: WBS – Case Study (cont’d)
Major Objectives (11):
Create a Web site that will provide basic trouble-shooting for common software applications supported by the TSU.
Include an FAQ section whose content will be provided by current Help Desk Group staff.
Develop and include information about good computing practices – backups, disk maintenance, etc. Help Desk Group will provide some videos for this.
Provide an online form for users to submit non-urgent requests to the help desk.
Include a help desk announcement page that informs users of current outstanding issues and status of resolution efforts.
Allow downloads of major releases of selected common applications as well as updates between major releases.
Make the site consistent in look-and-feel with the TSU main site.
Design the navigation for the site so that users can readily find needed information (particulars to be determined by prototyping).
Insofar as possible, design the site design so that editing of the site’s content does not impact its presentation, and vice versa.
Implement appropriate levels of security/access to the site’s information.
Ensure that the site adheres to current federal disability access laws and the company’s own access standards.

## Slide 83: WBS – Case Study (cont’d)
Initial Task List (21 items):
T1 Define site presentation
T2 Ensure consistency with current TSU site
T3 Choose design that ensures content/presentation separation
T4 Determine software applications to be included
T5 Get FAQ content
T6 Get computing practices content
T7 Plan for video for computing practice section
T8 Implement online form for non-urgent requests
T9 Include immediate feedback to requester
T10 Include periodic updates on progress re: online requests
T11 Define help desk announcement component
T12 Implement current release download page
T13 Implement software update page
T14 Ensure compliance with copyright laws
T15 Implement security levels
T16 Determine security levels needed (3 levels?)
T17 Define access/capabilities for each security level
T18 Implement and refine prototype to determine navigational interface
T19 Provide easy (form-driven) editing capabilities where possible
T20 Ensure compliance with disability access laws
T21 Ensure compatibility with company access standards

## Slide 84: Group Exercise
Evaluate each of these work products for the Web self-service case study we’re developing.
Do each of them accomplish what’s described above?
Would you change anything about any of these?
Which of these should be fixed at this point in the project?
The Business Need should be a fairly high-level description of the business problem to be solved
The Project Purpose is our response to the problem – what we intend to do to solve it (still high-level)
The Objectives provide specificity for the mission statement
The Task List is our (unorganized) identification of the tasks we believe are necessary for the accomplishment of the objectives (and hence the mission)
Before we continue to our WBS, let’s analyze the case study work so far. Remember that:

## Slide 85: WBS – Case Study (cont’d)
Initial WBS
Task List Organized with Coordinating and Other Tasks Added:
TSU Help Group Web Site Project*
Implement Presentation*
Implement Content*
Implement Security*
Ensure Legal/Standards Compliance*
T1
T2
T18
Get Req’mts*
T3
T19
T4
T5
T12
T13
C*
T6
T7
C*
T8
T9
T10
T11
T14
T20
T21
T16
T17
T15
C stands for a new Coordination task
* = new (not in original task list)

## Slide 86: Group Exercise
Assisting stakeholders in developing a clear vision of project deliverables
Modeling the overall process by which these deliverables will be managed and produced
Giving a graphical representation of project scope
Establishing a basis for accountability for project work
We have claimed that the WBS provides an excellent communication tool by:
Consider the WBS we just created. Could it do all these things?

## Slide 87: WBS – Case Study (cont’d)
We Can Expand the Initial WBS as Needed
(Progressive Decomposition of Work)
Hire Consultant
T3
Recommend Solution
Example:
Suppose we do not have the technical expertise in-house to accomplish T3
T3: Choose a design that ensures content/presentation separation
We might then choose to expand task T3 as follows:
Assess Req’mts
Acquire Software
Install Software
Get Approval
Create Design
Get Training
Test Design
Implement Design

## Slide 88: More on Critical Path Method (CPM)
Appendix C

## Slide 89: Creating CPM Diagrams
The Critical Path Method (CPM) is a schedule network analysis technique used to determine the amount of scheduling flexibility (the amount of float) on various logical network paths in the project schedule network, and to determine the minimum total project duration. Earliest start and earliest finish dates are calculated by means of a forward pass, using a specified start date. Latest start and latest finish dates are calculated by means of a backward pass, starting from a specified completion date, which is usually the project ‘s earliest finish date determined during the forward pass calculation.
Adapted from PMBOK® Guide

## Slide 90: Recall that CPM Diagrams Add Information to the PDM Diagram Nodes
Task
Earliest
Start
Earliest
Finish
Duration
Float
Latest
Start
Latest
Finish
Add this information for each node
in the Precedence Graph
Critical Path Method (CPM) Diagram
PDM Diagram

## Slide 91: Terms for CPM Diagrams
D = Estimated Duration for the Activity
ES = Earliest Start Date
  ES = Latest of the earliest finish date for all immediately preceding activities
EF =Earliest Finish Date
  EF = ES + D
LF =Latest Finish Date
  LF = Earliest of the latest start date of all immediately succeeding events
LS =Latest Start Date
  LS = LF - D
F = Float
  F = LF - EF OR F = LS - ES
Float is the time an activity’s start or finish can be delayed without delaying project completion
For each node:

## Slide 92: CPM Diagram Nodes – Example Calculations
Task
4 weeks
7 weeks
3 weeks
2 weeks
6 weeks
9 weeks
estimate duration
float (= 9 – 7 or = 6 – 4)
earliest start
(determined by
latest of the earliest
finishes for all immediately
preceding activities)
latest start
(= 9 – 3)
earliest finish (= 4 + 3)
latest finish (determined
by the earliest of the latest starts for all immediately
succeeding activities)
1
2
3
Step 1 should be done for all nodes before starting CPM calculations.
Next do steps 2 and 3 for ALL nodes during the forward pass. Start with those nodes with NO predecessors (this may be a single START node). Give these nodes a 0 earliest start.
Then do steps 4, 5, and 6 for ALL nodes during the backward pass. Start with those nodes with NO successors (this may be a single FINISH node). Give these nodes 0 float to get started.
Now you can identify the critical path (or paths) by marking all nodes with 0 float.
4
5
6

## Slide 93: Summary of Method for Computing CPM Diagrams
All activities must be assigned durations before you begin
Start with the activities that have no preceding activities and assign their earliest start times to be 0 (there may be only one of these). Calculate their earliest finish times by adding the duration to the earliest start times.
Work from left to right and compute the earliest start and earliest finish times for all nodes – this is called the forward pass
The largest of all earliest finish times will determine the minimum time for the project to complete
All activities with no succeeding activities will get this value as their latest finish times (there may be only one of these). Assign each of these activities to have 0 float
Use this information to work from right to left assigning latest finish times and latest start times for all nodes – this is called the backward pass
Now you can easily compute float for all nodes
Critical path (or paths) will be the sequence(s) of nodes with 0 float

## Slide 94: Putting It Together #C.1
Note that all activities already have estimated durations.
Note also that we’ve already assigned the activity that has no preceding activities (Feasibility) an early start time of 0.
Work from left to right and compute the earliest start and earliest finish times for all nodes. This is the forward pass. The minimum duration for the project will be the latest of the earliest finish times for the activities with no successors (in this case there is only one of these, namely Acceptance Test)
Now assign the activities with the latest of the earliest finish times (in this case just Acceptance Test) 0 float, which will also give it a latest finish time equal to its earliest finish time.
Now, work from right to left assigning latest finish times and latest start times for the remaining nodes. This is the backward pass.
Now calculate the float for all nodes.
This activity uses the CPM Diagram (partial) given on the next slide. Several copies are reproduced in the end of Appendix B for you to work with.

## Slide 95: CPM Diagram Example
Feasibility
Requirements
QA Plan
Design
Solicit Bids
Test Suite
Coding
Procurement
Beta Test
Deployment
Acceptance Test
0
1
5
2
3
4
3
4
2
3
4
2
Start
Finish
Activity
D
ES
EF
F
LS
LF
0
Legend

## Slide 96: Putting It Together #C.2
What is the minimum time to complete the project?
What is the critical path?
If Procurement slips 3 weeks, what is the impact on the project duration? What happens to the critical path?
If Beta Test slips 2 weeks (with no other slippage), what is the impact on the project duration?
Work in your team to consider the CPM Diagram that you completed in Putting It Together #C.1. Consider the last two questions independently of each other.

## Slide 97: Putting It Together #B.3
This activity continues with the project to plan and execute a company “celebration.” Each team should begin the activity with the consensus PDM network diagram that the group has agreed to earlier in Putting Together #4.
Recall your effort estimates for each activity, and decide on durations for each activity. Remember that effort and duration are not the same, so you have to make some resource allocation decisions and assumptions here. Your instructor will work with the group as a whole to do this.
Use the forward and backward pass technique to create a CPM Diagram for this project.
What is the minimum time required for the project (given your duration estimates)? In other words when is the earliest possible scheduling for the celebration event? In making this estimate, you should document your assumptions about the performance and availability of sub-contractors (caterers, speakers, etc.).
Identify the critical path(s) for the project.

## Slide 98: More on Earned Value Management (EVM)
Appendix D

## Slide 99: Using CPI and SPI for Projections Three Additional Terms
Budget at Completion (BAC) = total budget
Estimate at Completion (EAC) = estimate for total project (can be recomputed throughout the project – see next slide)
Estimate to Complete (ETC) = newly estimated remaining cost to complete the project from some given point

## Slide 100: Re-Computing EAC (Estimate at Completion)
A new EAC can be computed at any point in the project in several different ways, depending on assumptions we are willing to make:
  EAC = AC + ETC -- use this method when original estimates have proven to be flawed and are no longer relevant to changing conditions. Note that this makes use of a new estimate in ETC.
  EAC = AC + (BAC – EV) -- use this method when current variances are seen as an anomaly that we don’t expect to continue. Note that BAC – EV = the remaining budget.
  EAC = AC + [(BAC – EV)/CPI] -- use this method when current variances are seen as typical of future variances. Note that the term (BAC – EV)/CPI represents the remaining budget normalized for the currently observed cost performance index.
Re-estimate
Make up for variances
Adjust for variances

## Slide 101: Putting It Together D.1
Suppose your analysis of the main difficulties the project has experienced indicates that these issues are an anomaly. Further, you are convinced that the underlying problems have been corrected, and so you don’t expect them to continue. What new estimate for the total project budget would you give your manager, based on what you know now?
Suppose your analysis of the main difficulties the project has experienced indicates a different result – that the problems are endemic to this project and will continue. How does this change the new estimate for your manager?
Consider again the project that you have just received updated progress reports on. Recall that the project’s budget is 2000 hours. Your project plan calls for you to have completed work at this point in time which was budgeted to require a total of 800 hours. The work that you have so far completed was budgeted for a total of 600 hours. The number of hours you have charged against the project budget to date is 900. Your manager has asked you for a revised estimate for the total cost of the project.

## Slide 102: PMP Style Questions Some Practice Exercises
Appendix E

## Slide 103: Exercise #1
You are taking over a project and determine the following: Task B has an early finish of day 3, a late finish of day 6, and an early start of day 2. Task L is being done by a hard-to-get resource. The CPI is 1.1 and the SPI is .8. Based on this information what would you be more concerned about?
Float
Resources
Cost
Schedule

## Slide 104: Exercise #1
You are taking over a project and determine the following: Task B has an early finish of day 3, a late finish of day 6, and an early start of day 2. Task L is being done by a hard-to-get resource. The CPI is 1.1 and the SPI is .8. Based on this information what would you be more concerned about?
Float
Resources
Cost
Schedule

## Slide 105: Exercise #2
The ______ is a technique used to predict project duration by analyzing which sequence of activities has the least amount of scheduling flexibility.
Critical path method
Flow chart technique
Precedence diagramming method
Work breakdown structure

## Slide 106: Exercise #2
The ______ is a technique used to predict project duration by analyzing which sequence of activities has the least amount of scheduling flexibility.
Critical path method
Flow chart technique
Precedence diagramming method
Work breakdown structure

## Slide 107: Exercise #3
A project has three critical paths. What difference does this make to the project?
None, a critical path shows how long the project should take.
It increases the project risk.
It requires more people.
The situation is not possible.

## Slide 108: Exercise #3
A project has three critical paths. What difference does this make to the project?
None, a critical path shows how long the project should take.
It increases the project risk.
It requires more people.
The situation is not possible.

## Slide 109: Exercise #4
Your customer notifies you that the project must be completed two weeks earlier. What do you do?
Tell them that the project’s critical path does not allow the project to be finished earlier.
Tell your boss.
Meet with the team and look for options for crashing or fast tracking the critical path.
Work hard and see what the project status is next month.

## Slide 110: Exercise #4
Your customer notifies you that the project must be completed two weeks earlier. What do you do?
Tell them that the project’s critical path does not allow the project to be finished earlier.
Tell your boss.
Meet with the team and look for options for crashing or fast tracking the critical path.
Work hard and see what the project status is next month.

## Slide 111: Exercise #5
In trying to get the project completed faster, the project manager looks at the cost associated with crashing each task. A more complete approach to crashing would be to also look at ______:
The risk impact of crashing each task
The customer’s opinion of what tasks to crash
The day of the week the task is to take place
The project phase in which the task is due to occur

## Slide 112: Exercise #5
In trying to get the project completed faster, the project manager looks at the cost associated with crashing each task. A more complete approach to crashing would be to also look at ______:
The risk impact of crashing each task
The customer’s opinion of what tasks to crash
The day of the week the task is to take place
The project phase in which the task is due to occur

## Slide 113: Exercise #6
A project manager is trying to coordinate all the tasks on the project and has determined the following.
Task 1 can start immediately and has an estimated duration of 1 week. Task 2 can start after task 1 is completed and has an estimated duration of 4 weeks. Task 3 can start after task 2 is completed and has an estimated duration of 5 weeks. Task 4 can start after task 1 is completed and must be completed when task 3 is completed. Its estimated duration is 8 weeks.
What is the critical path duration for this project?
10
11
14
8

## Slide 114: Exercise #6
A project manager is trying to coordinate all the tasks on the project and has determined the following.
Task 1 can start immediately and has an estimated duration of 1 week. Task 2 can start after task 1 is completed and has an estimated duration of 4 weeks. Task 3 can start after task 2 is completed and has an estimated duration of 5 weeks. Task 4 can start after task 1 is completed and must be completed when task 3 is completed. Its estimated duration is 8 weeks.
What is the critical path duration for this project?
10
11
14
8

## Slide 115: Exercise #7
Based on the data in the previous question, if task 4 takes 10 weeks, what is the critical path duration?
10
11
14
8

## Slide 116: Exercise #7
Based on the data in the previous question, if task 4 takes 10 weeks, what is the critical path duration?
10
11
14
8

## Slide 117: Exercise #8
EAC is a periodic evaluation of:
Cost of work completed
Value of work performed
Anticipated total cost at project completion
What it will cost to finish the job

## Slide 118: Exercise #8
EAC is a periodic evaluation of:
Cost of work completed
Value of work performed
Anticipated total cost at project completion
What it will cost to finish the job

## Slide 119: Exercise #9
If EV = 350, AC = 400, PV = 325, what is CV?
25
-25
50
-50

## Slide 120: Exercise #9
If EV = 350, AC = 400, PV = 325, what is CV?
25
-25
50
-50

## Slide 121: Exercise #10
A CPI of .89 means:
At this time, we expect the total project to cost 89% more than planned.
When the project is completed we will have spent 89% more.
Your project is only progressing at 89% of that planned.
Your project is only getting 89 cents out of every dollar invested.

## Slide 122: Exercise #10
A CPI of .89 means:
At this time, we expect the total project to cost 89% more than planned.
When the project is completed we will have spent 89% more.
Your project is only progressing at 89% of that planned.
Your project is only getting 89 cents out of every dollar invested.

## Slide 123: Exercise #11
A SPI of .76 means:
You are over budget.
You are ahead of schedule.
You are only progressing at 76% of the rate originally planned.
You are only progressing at 24% of the rate originally planned.

## Slide 124: Exercise #11
A SPI of .76 means:
You are over budget.
You are ahead of schedule.
You are only progressing at 76% of the rate originally planned.
You are only progressing at 24% of the rate originally planned.

## Slide 125: Exercise #12
Which of the following is not needed in order to come up with a project schedule and cost estimates?
WBS
Network Diagram
Risks
Change control procedure

## Slide 126: Exercise #12
Which of the following is not needed in order to come up with a project schedule and cost estimates?
WBS
Network Diagram
Risks
Change control procedure

## Slide 127: Exercise #13
During the execution of a project, a large number of changes are made to the project. The project manager should:
Wait until all changes are known and print out a new schedule
Make changes as needed but retain the schedule baseline
Make changes as needed
Talk to management before any changes are made

## Slide 128: Exercise #13
During the execution of a project, a large number of changes are made to the project. The project manager should:
Wait until all changes are known and print out a new schedule
Make changes as needed but retain the schedule baseline
Make changes as needed
Talk to management before any changes are made

## Slide 129: Exercise #14
You are a project manager for a new building design project and have just received a project charter. You can create a detailed project schedule only after:
A project plan is created
A WBS is created
A budget is created
A project control plan is created

## Slide 130: Exercise #14
You are a project manager for a new building design project and have just received a project charter. You can create a detailed project schedule only after:
A project plan is created
A WBS is created
A budget is created
A project control plan is created

## Slide 131: Exercise #15
A project sponsor has been holding team meetings during project planning to get a project underway. Then the company hires a new project manager for the project. Who should be in control of the project during project planning?
The project manager
The team manager
Functional manager
The project manager’s boss

## Slide 132: Exercise #15
A project sponsor has been holding team meetings during project planning to get a project underway. Then the company hires a new project manager for the project. Who should be in control of the project during project planning?
The project manager
The team manager
Functional manager
The project manager’s boss

## Slide 133: Final Check -- Key Learning Outcomes
When you complete this course you will be able to:
Explain the uses and importance of a WBS
Show how a WBS can be used for bottom-up estimating
Describe three other methods for estimating
Describe how a WBS illustrates a progressive decomposition of work
Describe the steps required to move from a WBS to a project schedule
Explain what activity sequencing is and how it relates to schedule development
Explain the difference between effort and duration in schedule development
Describe a PDM diagram and its uses
Define what is meant by a critical path for a project
Define the CPI and SPI measures of project performance and progress and explain how they are used in analyzing the current state of a project
Describe the techniques called crashing and fast tracking
Define what is meant by earned value management
Identify the various processes, and how they relate, that lead to a project schedule, starting with the project requirements