## Slide 1: Estimating

## Slide 2: Cost Management
According to the PMBOK® Guide, Project Cost Management knowledge area includes the processes involved in planning, estimating, budgeting, financing, funding, managing, and controlling costs to complete the project within the approved budget
There are three constituent Cost Management processes in the Planning process group
  Plan Cost Management
  Estimate Costs
  Determine Budget
The 4th Cost Management process is called Control Costs and by its name it is clear that it is included within the Monitoring/Controlling process group

## Slide 3: Note on Cost Management
We should note that such things as the level of accuracy to be used for cost estimates, the units of measure (for example, hours, days, weeks, etc. for effort), the control accounts to be used in conjunction with the WBS (if applicable) are all environment specific and hence will not be a part of our discussion

## Slide 4: Common Sources of Project Cost
Labor
Materials
Subcontractors
Equipment & facilities
Travel

## Slide 5: Types of Costs
Direct Vs. Indirect
  Direct – assigned to the project that generate the cost: Labor & material
    Total Direct labor costs = (direct labor rate)(Total labor hours)
  Indirect – Overhead and General and Admin (utilities, taxes, insurance, travel etc)
Recurring Vs. Nonrecurring
  Recurring- continue over project life cycle
  Nonrecurring - once at beginning or end such as marketing analysis
Fixed Vs. Variable
  Fixed do not vary with usage- capital equipment lease
  Variable – increase through usage
Normal Vs. Expedited
  Expedited are unplanned costs incurred when steps are taken to speed up a project’s completion such asovertime or adding temp or contract workers

## Slide 6: Cost Estimation
Ballpark (order of magnitude) ±50%
  Used when time is or information is scarce
Comparative ±15%
  Assumption that historical data can be used as a frame of reference (parametric)
Feasibility ±10%
  Routinely used for construction projects. Developed after design work
Definitive ±5%
  Can only be given upon completion of most design work at a point when the scope and capabilities are well understood.

## Slide 7: Estimating
The PMBOK® Guide identifies important estimating techniques
  Analogous estimating
  Parametric estimating
  Function Point
  Bottom-up estimating
  Three-point estimating
All can be useful depending on the circumstances

## Slide 8: Analogous (Top-Down) Estimating
Analogous estimating uses information from previous similar projects as a basis for estimating the current project
When estimating costs, the technique relies on the actual costs of previous similar projects (not the estimated costs) as a basis for estimating the cost for the current project
Of course some adjustments may need to be made when applying historical information to the current project which will be in many ways different from any project done before
Analogous cost estimating while generally less costly and less time-consuming to apply than other techniques, is also generally less accurate
It may be more useful in the earlier phases of the project then later phases, when we have more project information available

## Slide 9: Parametric Estimating
Parametric estimating uses a statistical relationship between historical data and other variables called parameters to calculate estimates for activities.
These parameters might include such things as square footage in building construction, or lines of code in software development
This technique can produce more accurate estimates than analogous estimating provided that the underlying data built into the statistical model being used is accurate and applies to the current project

## Slide 10: Function Point Estimation
Function Point Analysis is a system for estimating the size of software projects based on what the software does.
Function points are a standard unit of measure that represents the functional size of a software application.

## Slide 11: Complexity Weighting Table for Function Point Analysis
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall

## Slide 12: Function Point Calculations for Restaurant Reorder System
Copyright © 2013 Pearson Education, Inc. Publishing as Prentice Hall
Our organization estimates that each resource can perform 10 FPs per man month. 409/10 = 40.1. If we assign 4 programmers it would take 10 person months. 10 programmers would take about 4 months.
If our avg. resource cost per programmer is 5k per month then our estimated cost for completing the job is about $200,000.
Not an exact science.

## Slide 13: Bottom-Up Estimating
Bottom-up estimating is one of the most common and most reliable methods of estimating
Its use depends on having a good understanding of the components of the work to be done
As we have seen, the WBS is a primary artifact used in bottom-up estimating
Recall that the advantage this approach accrues from the progressive decomposition we do in a WBS because it is usually much easier to estimate the cost of work packages accurately, than to estimate larger work components accurately
The accuracy of the method is further improved when we get the people who will actually be responsible for the work being estimated involved in providing the estimates

## Slide 14: Three-Point Estimating
The three-point estimating technique relies on taking a weighted average of three separate estimates
Usually you would employ (4*ML +O + P)/6
  A most likely estimate
  An optimistic estimate
  A pessimistic estimate
A popular technique that employs three-point estimating is PERT (Program Evaluation and Review Technique), pioneered by the US Navy in the Polaris Submarine Missile Program. PERT calculates an expected project activity cost using such a weighted average.

## Slide 15: Contingency Reserves
An additional tool that can be used in estimating costs is called reserve analysis
This usually includes including contingency reserves to account for the uncertainty in cost estimation.
Such reserves can be calculated as a percentage of the total estimated cost (often called management reserves)
As better information about the project becomes available, the contingency reserve may be used or reduced or even eliminated
When this tool is used, contingencies should be clearly identified as such in the cost documentation.

## Slide 16: Budget Contingencies
Contingencies are needed because
Project scope may change
Murphy’s Law is present
  Anything that can go wrong, will go wrong.
Cost estimation must anticipate interaction costs
Normal conditions are rarely encountered

## Slide 17: Cost of Quality
A possible input for cost estimating are assumptions about the cost of quality (COQ)
There are two major categories of quality, called the cost of conformance and the cost of nonconformance
The cost of conformance is estimated based on the activities in the project designed to create a quality product
The cost of nonconformance, which includes such things as rework or scrap work, is very difficult to estimate and is often overlooked when project costs are estimated
However, it is wise to include some assumptions about the cost of nonconformance in the original project cost estimates, especially in software projects

## Slide 18: Outputs of the Estimate Costs Process
There are two major outputs for the Estimate Costs process
  Activity cost estimates
  The basis for these estimates.
The basis for the estimates should include enough supporting documentation to indicate clearly how cost estimates were derived
This allows those using the estimates to better understand their possible accuracy

## Slide 19: Updating Estimates
Cost estimates should be refined throughout the project as more information about the project work becomes available
As a rough rule of thumb, cost estimates given early in the project life cycle -- rough order of magnitude (ROM) estimates -- could have an accuracy range of as much as plus or minus 50%
  This means an estimate of 10,000 hours could be reflected by an actual cost anywhere in the range 5,000 to 15,000 hours
Later as project information improves, cost estimates should converge toward a plus or minus 10% accuracy range
  This means a 10,000 hour estimate could be reflected by a true cost of between 9,000 and 11,000 hours
Organizational environments will differ as to what accuracies are acceptable at various points in a project
The project sponsor’s sensitivity to estimate accuracy will always be a factor too, of course

## Slide 20: Problems with Cost Estimation
Low initial estimates
Unexpected technical difficulties
Lack of definition
Specification changes
External factors

## Slide 21: Determining a Budget
The Determine Budget process basically combines, or aggregates, the estimated costs of individual activities or work packages
The primary inputs for the Determine Budget process are:
  Activity cost estimates
  Associated basis of those estimates
  Scope baseline containing
    Scope statement
    Work breakdown structure (WBS)
The main output of the Determine Budget process is the establishment of an authorized cost baseline for the entire project
This baseline includes all authorized budgets, but excludes any management reserve
Cost performance in the project will always be measured against the authorized cost baseline