## Management Information Systems, 13E

## Laudon & Laudon

## Lecture Files, Barbara J. Ellestad

# Chapter 14 Managing Projects

Previously, we discussed how to design and build information system projects. That may be the easy part. It’s much more difficult to manage an entire information system project to make sure a company realizes the intended benefits from its investment and that the system solves problems for the organization rather than create more.

# 14.1 The Importance of Project Management

Why do so many information system projects fail to deliver on their promises? Is it because the hardware, software, and data are flawed? Is it because user interfaces don’t allow people to perform their jobs correctly? Is it because the processes aren’t designed correctly? Those are all possibilities.

## Runaway Projects and System Failure

The statistics provided in the Laudon text are startling:

- One-half of private sector projects are underestimated in terms of budget and time required to deliver.

- A large number of projects are delivered with missing functionalities.

- Only 32 percent of all technology investments are completed on time, on budget, and with all the promises met.

- Between 30 and 40 percent of software projects far exceed their original schedules and budget projections.

What is the leading cause of these dismal statistics? In two words—project management. Figure 14-1 lists the consequences of poor project management.

Figure 14 -1 Consequences of Poor Project Management

Interactive Session: Management: Austin Energy’s Billing System Can’t Light Up (see page 531 in the text) describes how poor and inadequate project management led to disastrous results. The company has experienced severe delays in implementing a new system, errors in thousands of utility bills, costly overruns, and still doesn’t have a system that meets expectations and specifications.

## Project Management Objectives

Information system projects range from very small, end-user development projects to major implementations of enterprise systems. Regardless of size, they all have some common characteristics.

First, they require the effective use of project management tools and technologies that help keep the project on time, within budget, and meet objectives. Every project includes the same five variables:

- Scope: What work is or is not included in a project?

- Time: Establish timeframes for each component of a project.

- Cost: The amount of time multiplied by the cost of human resources required of a project.

- Quality: Does the project improve organizational performance and decision making?

- Risk: Potential problems that may threaten the project’s success.

Bottom Line: The statistics for successful implementation of information systems are dismal. The leading cause of so many project failures is the lack of proper project management. Every project includes five variables that must be adequately managed to help ensure success: scope, time, cost, quality, and risk.

# 14.2 Selecting Projects

“Gee, we thought we did everything by the book. Why doesn’t the system work the way we envisioned?” Perhaps it’s not the system itself but the way changes in the organization were managed. This section will help you better prepare for the hardest part of building information systems—managing the development and implementation of the system and the people it will affect.

## Management Structure for Information Systems Projects

To help ensure success, companies should have four levels of management control for system projects:

- Corporate strategic planning group: develops strategic plans.

- Information systems steering committee: includes department heads that represent end-users and information systems departments; reviews and approves systems plans, coordinates and integrate systems, selects specific projects.

- Project management: information systems managers and end-user managers; oversees specific information systems projects.

- Project team: directly responsible for individual system projects; consists of systems analysts, end-user business specialists, application programmers, and database specialists.

As you review the list above, one thing you should notice in particular is that there are business specialists and end-user involvement in every level of management. Too many companies fail to include nontechies in systems planning and management, much to their dismay later on.

## Linking Information Systems to the Business Plan

Companies buy the hardware they think is necessary for a new or improved information system. Then they purchase some software to go along with the new hardware. Now they realize their hardware is inadequate for the new software, so they buy more powerful hardware. And the vicious circle continues. Pretty soon they have a whole bunch of hardware and a lot of expensive software, but do they have an information system? Only if they have made sure all the hardware and software purchases fit in with their organizational information systems plan and their people know how to use them.

“A what?” you say. “Another plan that stifles creativity and creates roadblocks to getting work done?” No, a good information plan will help companies systematically figure out what they need to get the job done and whether all the hardware and software is necessary and if they really do meet the requirements of the organization. A good information plan will also take personnel needs into account and help determine how all three elements of the triangle will work together for success.

The problem is that too many companies don’t have a plan for integrating new hardware and software purchases into their overall business plan, let alone meshing them with the persware side of the triangle.

Of course, the information plan should support the overall business plan and not conflict with it. The plan must include all levels of the organization, including the strategic and executive levels. These two levels include the people who often say they are exempt from having to determine information system needs.

## Information Requirements and Key Performance Indicators

Key performance indicators (KPIs) are simply the goals managers feel will make the organization a success. Using this method broadens the scope of the analysis to include entire industries, the broader environment, in addition to the firm itself and its managers. That’s why it’s also called a “strategic analysis.” Basically, you contact several top managers, ask them what they think will make the organization succeed, and then combine the results into a cohesive picture.

## Portfolio Analysis

## Figure 14-3: A System Portfolio

The portfolio analysis shown in this figure allows a company to objectively rate multiple alternative projects for their risk and potential benefits. Companies too often get locked into just one idea without understanding that multiple choices exist. There is always more than one way to meet the organization’s goals.

The ideal situation is to choose a system with the highest benefit and the lowest risk while ignoring systems with the lowest benefit and highest risk. That’s reasonable. This method of rating projects helps companies align their IT assets with their business strategy and results in a better organization-wide coordination of IT investments.

## Scoring Models

The scoring model is effective for comparing various alternatives in terms of their costs. This model can go a long way toward helping organizations determine the best course of action and quantify their decision making. And, if nothing else, it creates a dialog among the managers about strategic factors they should consider for the good of the firm. As the text states, “Scoring models are used most commonly to confirm, to rationalize, and to support decisions, rather than as the final arbiters of system selection.”

Bottom Line: An appropriate management structure must be established for information systems projects at the senior, middle, and operational management levels. Information systems plans help link systems projects to the business plan. Critical success factors, portfolio analysis, and scoring models help organizations choose appropriate IT projects.

# 14.3 Establishing the Business Value of Information Systems

Just as you can analyze the benefit of purchasing a new piece of equipment for your business, you can analyze the impact of an information system. Think about it: You tell the boss you need a new storage system for all the widgets you are producing. The boss will ask you to complete some type of analysis to see how the bottom line will be affected. The same is true for a new information system. Just how will it benefit the business overall? What benefits will your customers gain from the new system?

However, you can’t reduce everything to dollars and cents. Sometimes the benefits of the new system will be measured in other ways, but you can employ several different methods to evaluate a new information system, just as you would a new storage system.

## Information System Costs and Benefits

One of the more difficult choices to make when evaluating new systems is to determine the tangible benefits vs. intangible benefits. When a financial institution must decide whether to offer online banking, it may evaluate the system using one of the methods outlined in the text and determine that it will cost half a million dollars to implement. The immediate cost savings of not having employees interface directly with customers may be only $250,000. On the surface you could say that the new system isn’t worth the cost—the bank will lose $250,000. But the intangible benefits the bank customers may enjoy could potentially be worth a million dollars. In that case, the new system’s intangible benefits will far exceed the tangible benefits. Table 14-3 in the text explains some of the tangible and intangible benefits of information systems.

### Capital Budgeting for Information Systems

There are several methods for analyzing a new system in terms of dollars and cents using capital budgeting techniques. Each method measures the financial worth of the system by determining the difference between cash outflows and cash inflows. The Learning Tracks on the Web site for this chapter helps you see how each method analyzes a proposed new system from a different perspective. Why not just have one, you might ask. Because in this case, one size does not fit all.

Financial models used to evaluate new systems are:

- Payback Method: time required to pay back the initial investment.

- Accounting Rate of ROI: approximation of the accounting income earned.

- Net Present Value: amount of money an investment is worth, taking into account its cost, earnings, and the time value of money.

- Internal Rate of Return: rate of return or profit that an investment is expected to earn.

## Real Options Pricing Models

The system investment that looks good to one company may be all wrong for another company based strictly on the numbers. That’s because no two companies are exactly the same. And the uncertainty of most IT projects makes it even more difficult to evaluate a project based solely on numbers. Real options pricing models offers strategic planners the ability to bring other factors into the evaluation and place a value on them. It uses these factors:

- Value of the underlying IT asset.

- Volatility of the value.

- Cost of converting the option investment into the underlying asset.

- The risk-free interest rate.

- The options’ time to maturity.

## Limitations of Financial Models

Keep in mind that there are limitations to each financial model used to evaluate new systems. Using the online banking example, you can assume the initial cost will not be recouped until months or years after implementation. As we’ve seen in the last few years, the hardware costs can change drastically within a short period of time. As soon as the system is installed, new technology can render it obsolete. How do you factor those realities into a financial evaluation model? Most of the time you can’t.

On the other hand, you’ll remember that the costs of adding new users to an existing network is marginal according to Metcalfe’s Law and Network Economics. That must be factored into the financial models as well as elements of the TCO (Total Cost of Ownership). It is not unusual for the personnel costs in the TCO model to be underestimated or even totally overlooked.

Bottom Line: Potential new systems should be evaluated in terms of tangible and intangible costs. All costs—hardware, software, and personnel—should be included in the bottom line so that the organization can truly determine the gains, or losses, associated with new projects.

# 14.4 Managing Project Risk

There’s a risk to every project—large and small. Ignore those risks and you’re simply asking for failure.

## Dimensions of Project Risk

Here are three dimensions of risk associated with every project:

- Project size: As projects grow larger, the associated risk of failure increases. It’s not just technical complexity that jeopardizes large projects. The number of units and groups that will use the new system and the potential influence the project has on business processes affect risk.

- Project structure: Are requirements clear and straightforward or are they undefined, fluid, and constantly changing? Are users constantly changing their ideas about what the system should do? Do users even agree on what they want the new system to do?

- Experience with technology: Will the project team and information system staff have to learn new skills associated with the new system? If so, that will expose the project to technical problems and probably take more time to implement.

## Change Management and the Concept of Implementation

Change is a given element in the business world. From mergers and acquisitions, to complete corporate purchases, to changing work processes and methodologies within the same company, change is hard on people and organizations. But change management is one of those necessary evils that keep companies in the lead or helps destroy them.

### The Concept of Implementation

Implementation of a new system is not just about how to put the hardware and software into place. You have to address and manage people and processes to make sure they are in sync with the hardware and software. In essence you become a change agent. You have to convince users that the system is going to improve their world and that the new will be better than the old. If people are going to lose their jobs because of the new system or if they are going to experience a significant difference in responsibilities, you must be clear in communicating those changes to them.

### The Role of End Users

Make users feel they own the new system instead of it being an enemy or something they should fear. That’s why we stress user involvement through the entire development process. The new system shouldn’t be a surprise on Monday morning! Familiarity doesn’t always breed contempt; it should breed acceptance when it comes to new information systems.

Table 14-4 gives you good insight into the user-designer communications gap. As a manager, your job is to bridge that gap to help ensure success of the new system. Too little discussion and communication between the techies and the nontechies will be apparent through design flaws and a poorly implemented project. Understand where both sides are coming from, and you'll do a better job of getting them to work together. You can never have too much communication.

### Management Support and Commitment

If managers don’t like the new system or fear it, then how in the world can you expect the workers to accept it? The best way to get managers to like, support, and fund the new system is to communicate with them every step of the way. Make sure they know what’s going on. After all, managers are people too, and they have the same fears as anyone else.

Management support and commitment for new projects is required for these reasons:

- Creates a positive perception for both users and technical information services staff.

- Ensures sufficient funding and resources are devoted to the project.

- Implementing changes in work habits and procedures are easier.

- Enforcing organizational realignments.

### Change Management Challenges for Business Process Reengineering, Enterprise Applications, and Mergers and Acquisitions

The text gives the startling fact that 70 percent of all business process reengineering projects fail to deliver promised benefits. It doesn’t have to be that way. One abiding theme in most of the failures and successes is people. If the changes required by and in people are managed properly, then the success rate increases. Conversely, if people are poorly managed or, just as likely not managed at all, then the project stands a good change of failing. The leading threats of BPR projects are:

- Dealing with fear and anxiety throughout the organization.

- Overcoming resistance by key managers.

- Changing job functions, career paths, and recruitment practices.

- Training.

In spite of the size of the information system, some kind of organizational change must take place. Even if the project only involves two people, they will have to do things differently. As projects grow in size and scope, organizational change will grow accordingly.

Remember when you moved in with your college roommate? Or perhaps you got married. Or maybe you’re sharing an apartment with someone. Maybe you had to move your favorite chair to another room to accommodate the other’s large-size sofa. Or perhaps your microwave was different than your spouse’s, therefore he had to learn a new way to operate yours. Regardless of the circumstances someone had to change the way they do things. The same thing happens in the business world when two companies merge.

The business world is fraught with examples of mergers and acquisitions that didn’t work out or were not cost-effective. Many of the problems can be traced to employees who didn’t adapt to the changes or to poorly integrated systems. To ensure a successful merger managers must recognize:

- The realistic costs of integration.

- The estimated benefits of economies in operation scope, knowledge, and time.

- Any problematic systems that require major investments to integrate.

- Any likely costs and organizational changes required to upgrade the IT infrastructure.

## Controlling Risk Factors

Identify the nature and level of risk associated with the project first. Then you can use the appropriate tools and risk-management approaches to reduce the risk of the project failing.

### Managing Technical Complexity

You can use special tools to help you manage the implementation of a new information system (internal integration tools). It’s important that the project leaders and team members have the appropriate level of expertise and experience in the project’s technology. Otherwise, you should obtain it from outside sources.

### Formal Planning and Control Tools

Automated management tools such as PERT or Gantt charts (formal planning and control tools) can also help you manage a complex project. They are extremely beneficial for scheduling events and tracking the hundreds of details involved.

Compare Figures 14-4, Gantt Chart, and 14-5, PERT Chart, in the text to understand the difference between the two types of planning tools. The Gantt chart depicts all of a project’s activities, showing the start date and the anticipated completion date. It also lists the personnel resource requirements needed for each task. PERT charts on the other hand, show the interrelationship between tasks. It’s a great way to show which tasks must be completed before other tasks can begin.

### Increasing User Involvement and Overcoming User Resistance

We simply can’t say it enough! Get users involved from the very beginning of a project and keep them involved. Use external integration tools to keep people involved and informed. Guard against destructive, although innocent, sabotage of the system (counterimplementation). Remember, people will weigh their own needs against those of the organization. You have to make sure the two agree as much as possible.

Some of the strategies you can use to overcome user resistance include:

- User participation.

- User education and training.

- Management edicts and policies.

- Better incentives for users who cooperate.

- Improve the end-user interface.

- Solve organizational problems before introducing a new system.

Interactive Session: Organizations: Westinghouse Electric Takes on the Risks of a “Big Bang” Project (see page 548 on the text) discusses the success one company experienced by using the right tools and technologies to manage projects. Most importantly, the company involved its employees throughout the project lifecycle and gave them a sense of ownership of the new system.

## Designing for the Organization

“Just what will this new system do for us?” That’s a very appropriate question but unfortunately, it’s often ignored. Everyone seems to get caught up in the hustle and bustle of the implementation process and they forget to address basic questions about the new system. An organizational impact analysis will help answer questions about organizational structure changes, attitudes, decision making, and operations. We urge you to write down what you want the end result to be in terms of the organization. If you do so, you can use these notes as the basis for your impact analysis. The analysis can also be a great communication tool to explain to people how their jobs will be affected, to explain the changes required, and to help them plan the individual efforts required for a successful new system.

How will the new system fit into the human element? That’s the idea behind ergonomics; getting human and machine to agree and complement each other.

### Sociotechnical Design

Unless you design a system that will be totally controlled and operated by robots, you must pay attention to the sociotechnical design of your system. Simply stated, this means how the technical aspects of your system will fit in with the human aspects.

## Project Management Software Tools

Because project management is so difficult, there are some great software programs you can use to help you manage projects regardless of their size. The programs automate many of the mundane tasks like defining tasks, assigning resources, establishing start and end dates, tracking progress, and creating and maintaining PERT and Gantt charts. Best of all, when one element of a project changes, it’s easy to see how other elements are affected. That will help you make better decisions about the project and keep track of the myriad of details.

If your organization has several projects in the works, managers should consider using project portfolio management software to help track the proposals and projects against budgets and resource capacity. The software also helps manage dependencies among the projects and helps executives and managers determine the optimal mix and sequencing of projects.

Bottom Line: How well changes in an organization caused by implementation of a new system are managed can spell success or failure. The causes of implementation success and failure are user involvement and influence, management support and commitment, controlling risk factors, and designing projects for the organization.

## Discussion Questions

- Why should you consider the intangible benefits of a new system when they are difficult to factor into a capital budgeting model?

- Discuss the difference between a portfolio analysis and a scoring model for evaluating projects from a strategic standpoint?

- What are some of the causes of implementation success and failure? Which one(s) do you think are the most important?

- Use one of the capital budgeting models discussed in the text to determine the cost of implementing a new system in your organization.

- Discuss how the User-Designer Communications Gap can cause a good project to go bad.

## Answers to Discussion Questions

- Intangible benefits of a new system may outweigh the negative results of a capital budgeting model and show the system to have greater benefits to customers and users than can be measured in dollars and cents.

- A portfolio analysis allows a company to objectively rate multiple projects for their risk and potential benefits. The scoring model is effective for comparing various alternatives in terms of their costs.

- Causes of implementation success and failure are user involvement and influence, the level of complexity and risk, management support and commitment, and management of the implementation process.

- Answers will vary depending on the project and method chosen.

- Answers should reference Table 14-4, The User-Designer Communications Gap, and include references to how the techies view projects differently than the nontechies.