## Slide 1: DIA Automated Baggage Handling System
MSNBC on Denver's Automated Baggage System

## Slide 2: Background
November 1989: Airport construction begins
Estimated Date of completion: October 1993
Estimated cost: 2 billion dollars
One of the largest and most technologically advanced airports in the world
  2X the size of Manhattan – 53 square miles
Selection of baggage handling system was initially the responsibility of each airline

## Slide 3: Background
United Airlines contracts with BAE to create an automated baggage handling system for their terminal
In 1991 – 2 years after construction began, airport officials realize that only United has begun the process of incorporating a baggage handling system
Officials approach BAE in order to discuss feasibility of an airport-wide automated baggage handling system

## Slide 4: Background
BAE contracts with airport officials to design and build an airport-wide baggage handling system for 193 million dollars to be completed within 21 months
Goals of the system
  Deliver each bag individually – including transfers – automatically from check-in or the unloading of the aircraft to the outward bound aircraft or baggage claim
  Maximum delivery times:
    Wide body aircraft – 30 minutes
    Narrow body aircraft – 20 minutes
  Designed to allow transport of baggage anywhere within the airport to or from the main terminal within 10 minutes
  Must move the baggage at a rate => the rate at which travelers move
  Deliver over 1000 bags per minute

## Slide 5: 3 Methods of Moving Bags
Tug & Cart
  Labor intensive
  Manual Method
Telecars
  Multiple luggage pieces in one cart
  Not automatically sorted
  Typically used in automated systems
DCV – Destination Coded Vehicles
  Each cart contains a single piece of luggage
  Automatically sorted
  Not typically used or well tested
  Little or no human interaction required
  Selected for the Automated Baggage System at DIA

## Slide 6: System Components
300 486-class computers distributed in eight control rooms
Raima Corp. database running on a Netframe systems fault-tolerant NF250 server
High speed fiber-optic Ethernet network
14 million feet of wiring
56 laser arrays
400 frequency readers
10,000 motors
92 PLCs to control motors and track switches
3,100 standard baggage carts (DCVs)
450 over-sized baggage carts (DCVs)
2,700 photocells
Over 17 miles of track
Over 6 miles of conveyors

## Slide 7: Functionality of original design
Check-in
  Bar code labels
    Bag’s owner
    Flight number
    Final destination
    Intermediate connections and airlines
  Automated bar code scanner
    Array of bar-code scanners arranged 360 degrees scan baggage
    Typically able to scan 90% of luggage
    Luggage unable to be scanned is routed to another conveyor to be manually scanned
  Theoretically after reading the bar-code, the system will know where that bag is at all times

## Slide 8: Baggage Handling Process
Conveyors
  Hundreds of conveyors with junctions connecting all of them
  Sort all of the bags from all of the different airlines and send them to DCVs that are headed to the proper terminal and gate
  Conveyor can only advance when there is an empty cart onto which the leading bag can be placed
  Conveyor speed depends on the rate of delivery of empty carts

## Slide 9: Baggage Handling Process
DCVs
  Metal cart with wheels on the bottom and a plastic tub on top (mounted on a pivot) that tilts into three positions for automatically loading, carrying and unloading baggage
  Ride on a metal track like a roller coaster
  Travel up to 24 mph
  Slow to 4.5 mph for loading and 8.5 mph for unloading
  Photo-electric sensors trigger laser scanner when DCV is present and associate the bag with the DCV
    Located every 150 to 200 feet of track
  Data from scanners is transmitted to a computer that translates it by using a look up table to match the flight number with the appropriate gate

## Slide 10: Baggage Handling Process
DCVs
  Tracking computer guides the DCV to its destination by communicating with the radio transponders mounted on the side of each DCV
  DCVs move via linear induction motors mounted approximately every 50 feet of track
  Tracked by computers
    Control PLCs
    Handle DCV merges into traffic
    Control track switches
    Monitor each of he system’s radio transponders
    Track gate assignments for potential re-routing
    Track obstructions or failures
    Automatically detour around a stalled vehicle or jammed track

## Slide 11: Baggage Handling Process
Two counter-circulating closed-loop tracks with multiple routing connections provide for future expansion and add redundancy to guard against unanticipated problems

## Slide 12: Baggage Handling Process
Decentralized computing allows the baggage system to operate independently of the airport's information systems department
Only dependence within the systems involves coordination with the airlines’ flight reservation and information systems

## Slide 15: Performance Tests
Bags fell out of the DCVs causing the system to jam
Even with a system jam, bags continued to be unloaded because the photo eye at that location could not detect the pile of bags on the belt and could not signal the system to stop
DCVs crashed into one another – especially at intersections
DCV didn’t appear when summoned
Baggage incorrectly loaded and misrouted
Bags were loaded into DCVs that were already full so some bags fell on the tracks causing the carts to jam because the system lost track of which DCVs were loaded or unloaded during a previous jam and when the system came back on-line, it failed to show the DCVs were loaded
Timing between the conveyor belts and the moving DCVs was not properly synchronized causing bags to fall between the conveyor and the DCVs. Bags became wedged under the DCVs which were bumping into each other near the load point.

## Slide 16: Result
Inadequate performance caused several delays in the airport’s opening totaling 16 months
Automated system was designed with no backup system in place
An additional 5 months was required to build a traditional tug and cart system at a cost of 51 million dollars
Debts came due prior to the airport’s opening costing the airport 1.1 million dollars day in interest and opportunity cost
Cost overrun totaled over 253 million dollars
Total Airport cost amounted to more than 4 billion dollars

## Slide 17: What went wrong?
Despite its importance, the baggage handling system was an afterthought
  The airport was 2 years into construction before the baggage system was considered
  The system would have to be retrofit into the airport as it was designed initially including narrow tunnels and tunnels with sharp turns making it extremely difficult to navigate the DCVs

## Slide 18: What went wrong?
The time constraint was impossible to overcome
  The 21 month schedule precluded extensive physical testing or simulation of the full system design

## Slide 19: More significant problems
Reliable Delivery
  System consists of over a hundred waiting lines that feed into each other
    Belt will only advance when there is an empty cart
    Empty carts will only arrive after they have deposited their loads
    Cascade of queues
  Pattern of loads on the system are highly variable
    Depend on the season, time of day, type of aircraft
    The number of possible scenarios is enormous

## Slide 20: More significant problems
  Misreads
    Compounded by the fact that not only are the scanners required to read data from the tags attached to the baggage, but the information must also be transmitted by radio to devices on each of the DCVs. This duality compounds the errors.

## Slide 21: More significant problems
Complexity
  System of this size providing time sensitive delivery of materials on such a large scale had never been done before
    12x as many carts traveling 10x the speed of carts typically used at that time
Not just an increase in complexity relative to current systems, but a leap in complexity
  System must track tens of thousands of bags going to hundreds of destinations – all in real time
  Distributed computer system
  In addition to regular error checking, software must guard against electrical disturbances in the communications, have multiple levels of redundancy and be able to recover from errors very rapidly

## Slide 22: More significant problems
Line-Balancing problem
  All lines of flow should have balanced service
  Need to have sufficient empty carts to accommodate the bags coming off the conveyor belt
  In a postmortem simulation, the inability of the system to provide adequate empty carts was the primary cause of its failure. A simulation was also completed prior to the start of the project, but due to a lack of communication, BAE was not notified by airport officials of the results; The results stated, in essence, that the system would not work as it was initially designed

## Slide 23: Solutions
Short Term
  Backup system
    Unfortunately didn’t exist in this case
    Reduce complexity (automate only outgoing bags)
Long Term
  Is it so complex that a reduction in complexity will mean unacceptable performance or cost-effectiveness

## Slide 24: Where is DIA’s automated baggage system today?
After 10 years and $600 million, the Denver airport goes back to reliable tugs and carts in 2005
Was the project feasible?
Video